## Slide 1: S&E and BMW Regional Operational Programmes 14 – 20 Training for Local Authorities involved in DUCGS projects, 21st April 2016 REPORTING, DATA COLLECTION & MANAGEMENT VERIFICATIONS
Sonja Maurus
Programme Executive Financial Management, Monitoring & Evaluation
Southern Regional Assembly

## Slide 2: OVERVIEW
  Reporting Requirements
  Data Collection Requirements
  Management Verifications

## Slide 3: 1) Reporting Requirements
Annual Implementation Report
  When: Once per year (in January) request for report on progress with project implementation relating to previous calendar year
  What: Report to contain project data in relation to:
  - Expenditure incurred during reporting year
  - Achievements (outputs) during reporting year
  - Any issues / difficulties affecting project performance experienced during reporting year
  - Progress towards Horizontal Principles
  - Examples for information & publicity actions

## Slide 4: 1) Reporting Requirements (2)
Annual Implementation Report (2)
  Who/When:
  Request will be sent by MA to LA including deadline for response (see section 10 grant agreement)
  Template for reporting will be provided by MAs.
  Timelines are important because strict deadline for submission of Programme Annual Implementation Report to EC.

## Slide 5: 1) Reporting Requirements (3)
Annual Implementation Report (3)
  Why: Legal basis: Articles 50 & 111 Regulation (EU) 1303/2013
  MA’s need to compile data from all schemes into Programme Annual Implementation Report for reporting progress with programme implementation to EC.
  Reports need to be approved by Programme Monitoring Committee before submission to EC.
  If the EC does not find the Annual Implementation Report admissible, EC can decide to interrupt interim payments to Member State.

## Slide 6: 2) Data Collection Requirements
Data to be recorded and stored in computerised form (Article 125(8) of Regulation (EU) No 1303/2013)
… for each operation
Delegated Regulation (EU) 480/2014, Article 24
Legal basis: Art. 125.8 CPR and Art. 24 & Annex III of Delegated Regulation (EU) 480/2014

## Slide 7: 2) Data Collection Requirements (2)
NEW IT System!
Expected to be operational towards end 2016 – interim arrangements until then
LAs required to record project data (financial & activity)

## Slide 8: 2) Data Collection Requirements (3)
List of data to be recorded and stored in computerised form in the monitoring system (referred to in Article 24)
113 fields in total
IT system will cover all relevant fields (less than 113!)
Examples for data to be recorded (list is not exhaustive):
Data on the beneficiary (legal status, VAT situation, contact details)
Data on the operation (project ref., description, start/end dates)
Data on categories of intervention (e.g. location)
Data on indicators (result & output, incl. targets and achievements, broken down by gender, if relevant)
Financial data (total eligible expenditure, total public expenditure as approved and actual costs)
Data on payment claims (date of receipt, date of payment, amounts, net revenue generated, date of verifications, date of audits,)
Data on expenditure in payment claim (incurred & paid, eligibility, contracts incl. procurement procedures, irregularities)
(Delegated Regulation (EU) 480/2014, ANNEX III)

## Slide 9: 2) Data Collection Requirements (4)
Use of data collected:
… take all necessary measures to prevent any unauthorised disclosure of, or access to, the data collected
… use the data collected for the sole purpose of fulfilling its responsibilities
… data collected shall not be sent to persons other than those in the Member States or within the Union institutions whose duties require that they have access to it in accordance with the applicable rules.
Delegated Regulation (EU) 480/2014, Article 26

## Slide 10: 3) Management Verifications
Purpose: Verify that the co-financed products and services have been delivered and that expenditure declared by the beneficiaries has been paid and that it complies with applicable law, the operational programme and the conditions for support of the operation.
Verification, not audit, but preparation for audits!
All expenditure declared to EC is subject to audit!
When: Before expenditure is declared to the European Commission through the Form B process
Who: - Managing Authority will carry out verifications
- LAs need to prepare documentation
LAs are responsible for ensuring that expenditure declared is legal and regular and complies with all applicable Union and national law.

## Slide 11: 3) Management Verifications (2)
What:
Management verifications to ensure, on the basis of the data reported by the beneficiaries, that both the claim itself and the relevant supporting documentation is available, complete and in compliance with the rules & regulations.
(Legal basis: Art. 125.4 Regulation (EU) 1303/2013)

## Slide 12: 3) Management Verifications (3)
Verifications cover in particular:
Expenditure relates to the approved project
Compliance with funding conditions in accordance with the grant agreement
Adequacy of supporting documents and existence of an adequate audit trail
Eligibility of the expenditure (incl. incurred & paid)
Compliance with Union and national public procurement rules
Compliance with Information & Publicity requirements
Compliance with State Aid rules, sustainable development, equal opportunity and non-discrimination requirements
That data related to indicators and target values is timely, complete and reliable.
Physical progress and delivery of the product / service
Review of Procedures Manual (requirement in accordance with grant agreement)

## Slide 13: 3) Management Verifications (4)
Procedure: Administrative & on-the-spot checks
- Administrative checks : 100% of claimed expenditure is verified
- On-the-spot checks: Carried out on sample basis
How:
Standardised checklist (joint procedures SRA & NWRA)
All verifications are recorded.
Findings & recommendations are communicated to the LAs.

## Slide 14: Contacts
NWRA : Brendan Mooney, Auditor
Tel 094 9877251, e-mail: bmooney@nwra.ie
Gerardine Lafferty, Asst. Staff Officer,
Tel 094 9877014, e-mail: glafferty@nwra.ie
SRA : Vincent Dunphy, Programme Executive
Tel.: 051 860700, e-mail: vdunphy@southernassembly.ie
(Waterford & Cork Gateways, Mallow, Ennis &Wexford Hubs)
Sonja Maurus, Programme Executive
Tel.: 051 860700, e-mail: smaurus@southernassembly.ie (Dublin & Limerick Gateways, Tralee & Kilkenny Hubs)

## Slide 15: THANK YOU!
ANY QUESTIONS?
Sonja Maurus
Programme Executive Financial Management, Monitoring & Evaluation
Southern Regional Assembly
O’Connell Street, Waterford
Phone: 051 860 700
E-mail: smaurus@southernassembly.ie
www.southernassembly.ie